## Feature Gap Analysis
Feature | Your Software | Competitor A | Competitor B | Notes
Attendance Module | Yes | Yes | Yes | Lacks automation features
Grading System | Partially | Yes | Yes | Partially implemented but needs improvement
Parent Portal | No | Yes | Yes | Not available; critical feature
Mobile App | No | Yes | Partially | Not available; high demand in market

## Rebuild vs Enhance Matrix
Criteria | Enhance Current | Rebuild | Score (1-10)
Cost | Medium | High | 7
Timeline | Short | Long | 5
Risk | High | Medium | 6
Long-Term Benefits | Low | High | 9

## Timeline Breakdown
Phase | Enhance (Weeks) | Rebuild (Weeks)
Analysis | 2 | 2
Design | 4 | 6
Development | 6 | 12
Testing | 2 | 4
Deployment | 1 | 2

## Risk Assessment
Risk | Likelihood (1-5) | Impact (1-5) | Mitigation Strategy
Migration Issues | 4 | 5 | Backup data regularly
Extended Timelines | 3 | 4 | Create realistic timelines
Increased Technical Debt | 5 | 5 | Refactor critical modules first
Unstable Functionality | 4 | 4 | Thorough testing with rollback plans